## Slide 1: Project Title
MILESTONES SCHEDULE
Activity
Past 30 days:
  MM/DD/YY Capture activity for past 30 days
  When past 30 days, delete line item
  Next 60 days:
  Capture activity for next 60 days with anticipated execution dates
  MM/DD/YY - ……
Name
Name
Name
Name
Name
Supplier Mgmnt PA:
MBU Sponsor:
Project Manager:
Equip. Engineer:
1st Line Manager:
F&AM Planner / PA:
Name
Status Date: XX/XX/2020
Project Description
  Describe project - replace, upgrade, expand, rate
  Number of assets; disposition of existing assets
  Asset utilization; SOW
  Dependencies - Linkage to other projects
Y
  Help Needed
  Identify help needed by whom
RFU | 
IMB | Current
MM/DD/YY | MM/DD/YY
Capital | Expense
MM/DD/YY | 2020
$00.000M | $0.000M
Risks / Issues / Comments
  Identify risks, issues, warning signs, mitigation concerns or comments
  Impact to scope, schedule, cost, safety
  Impacts to BCA program(s)
  Lessons learned
RFU Box
RFU date identified in original IMB
Current RFU Date
Date Capital committed
Committed Value
Current year expense value
Sponsor / Name
MBU Sponsor is primarily the senior area manager and is responsible for the project
Insert the name of the F&AM planner and change when a PA is assigned
IMB Approval
Mar 2018
RFQ
Jan 2019
Release PO
May 2019
RFU
4/10/20
May 2020
Bid Spec Approved
Nov 2018
F&AM Design Complete
1/22/19
Mar 2019
F&AM Construction Complete
Mar 2020
May 2020
Machine
On Dock
4/20/20
F&AM Scope and Layout Complete
Sept 2019
Nov 2019
FAT
3/20/20
CBR Number: AAMXXXX
Completed milestones - solid fill
Future milestones - no fill
Milestones slides - depicted in red and dashed
Spend
Layout
Other
IMB
On Plan
G
Y
No recovery plan in place
R
Recovery plan in place
Preliminary Plan
P
Fin Sum
Notes: History:
  Completed Vibro Deburr Layout – 7/16
  Cutter package ordered – 7/22
  Completed CMM Layout – 7/23
  Receive final foundation dwg from Starrag – 8/12
  Relocate CC1 Deburr Booth – Complete 8/29
  Time study for manual deburr – Complete 9/4
  Finalize CMM layout – Complete 9/17
  Finalize layout for manual, vibro and robotic deburr – Complete
  Finalize break area layout – Complete
  Phase 1 - Completed 11/5
  Phase 2 - Completed 11/8
  Phase 3A - Completed 11/22
  Phase 3B - Completed
  History (Issues):
  Cutter package order has been delayed multiple times.
  F&AM delays due to capacity.

## Slide 2: Spend Profile
- Insert Project Title
Chart: Spending Versus Cumulative
| 43466 | 43497 | 43525 | 43556 | 43586 | 43617 | 43647 | 43678 | 43709 | 43739 | 43770 | 43800 | 43831 | 43862 | 43891 | 43922 | 43952 | 43983 | 44013 | 44044 | 44075 | 44105 | 44136 | 44166 | 44197 | 44228 | 44256 | 44287 | 44317 | 44348 | 44378 | 44409 | 44440 | 44470 | 44501 | 44531
Capital Expedentures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93100 | 0 | 0 | 252750 | 422305 | 90900 | 45000 | 343000 | 186200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93100 | 93100 | 93100 | 345850 | 768155 | 859055 | 904055 | 1247055 | 1433255 | 1433255 | 1433255 | 1433255 | 1433255 | 1433255 | 1433255 | 1433255 | 1433255 | 1433255 | 1433255 | 1433255 | 1433255 | 1433255 | 1433255 | 1433255 | 1433255 | 1433255
Spend Profile
This information is provided by the Equipment Engineer to the PM for insertion into the file.

## Slide 3: Financial Summary
- Project Title
Financial Summary
This information is provided by the Equipment Engineer to the PM for insertion into the file

## Slide 4: Factory Layout
Insert factory layout
- Project Title

## Slide 5: Supporting Documentation
Insert Supporting Documentation
Add slides accordingly
  Load Charts
  Photos
  Maps
  RIO – Risk Management
  Critical Path
  A3 or problem solving documents
  etc
- Project Title

## Slide 6: IMB Presentation
Insert original IMB presentation
If additional funds has been committed, insert the IMB presentation
IMB Presentation

## Slide 7: Key Milestones
Key Milestones:
Acronym Milestone Definition
* IMB IMB Approval Verbal approval from IMB
Scope of Work Approved Affected parties agree to requirements and deliverables
* BSA Bid Specification Approved Affected parties approved bid specification
RFQ Release RFQ (Request for Quote) Purchase request submitted with defined requirements
Purchase Specification Approved Affected parties approved purchase specification
* PO PO Released (Purchase Order) Negotiations are complete and contract signed by Supplier Management and and the vendor
Key milestone expenditures Key payments on timeline based on contract terms and conditions
Equipment Design Review Complete Final design approved by affected parties, authorizing supplier to initiate fabrication
Requirements to SSG Asset, facility requirements and drawings submitted to SSG
Area layout complete
* CD F&AM Design Complete F&AM design
* RFI F&AM Construction / Utilities Complete Area ready for asset installation
                Asset removals or move
                Key construction milestones, e.g. foundations
* FAT Factory Acceptance Test Testing at supplier is complete and approved test documents are signed; authorization to ship
* O/D Asset On-dock Date asset is expected to be delivered to facility
Installation Complete Asset is assembled and run through tests to ensure readiness for acceptance testing. Supporting hardware, etc. in place for testing
BAT Final Acceptance Complete Boeing – Acceptance; Equipment meets specifications (Initiates final payment)
* RFU Ready for Use Asset is installed, functionally ready to use and is capable of running parts
Production Ready Qualifications, accreditation, testing and integration and training are complete. Tools are in place, production part plans in place, inspection plan in place. Operations has what is needed to start running production parts
* Required milestone on four square

## Slide 8: Timelines
Standard Schedule Timelines
One Year
Two Year
Three Year
Change the years and months as needed to adjust for the time period.
To change the completed segment of the timeline:
  Select the black box
  Right click on the selection
  Select “Size and Position”
  Under the format options, click on the up or down arrows to change the width of the box
  Note: The height of the box is set at 0.1 to fill in the space properly